## Summary
Metric | Value | Status | Notes
Project | Qrave QR menu and table-ordering SaaS | In progress | Multi-tenant restaurant/cafe SaaS.
Last updated | 2026-06-02 | In progress | Based on docs/PROJECT_CONTEXT.md and current repo state.
Completed phase count | 6 | Completed | Foundation through local demo smoke testing are complete.
Pending phase count | 5 | Pending | Integration testing, deployment readiness, staging, production, and post-launch improvements.
Immediate next step | Validate current uncommitted changes, then commit | In progress | Run backend tests and frontend build; review next-env.d.ts before committing.
Next project milestone | SQL Server integration test suite | Pending | Covers stored procedures and critical API/database workflows.

## Phase Plan
Phase | Area | Status | Completed Deliverables | Pending Work | Priority | Estimated Effort | Dependencies | Notes
0 | Project setup and architecture | Completed | Repo docs, clean architecture backend skeleton, ASP.NET health endpoint, Next.js/Tailwind frontend skeleton, SQL folder structure, Docker setup, solution file. | None for foundation. | High | Completed | None | Baseline created.
1 | Database and backend foundation | Completed | Tenants, branches, branch settings, menus, tables, QR tokens, orders, waiter calls, indexes, stored procedures, ADO.NET repositories, SQL error mapping. | Production migration runner still pending in later phase. | High | Completed | Phase 0 | Stored procedure only data access pattern established.
2 | Authentication and admin foundation | Completed | Owner registration, login, PBKDF2 password hashing, JWT auth, tenant context, protected admin APIs, admin login/branch workspace UI. | Legacy foundation tenantId route APIs still exist and should be removed or hidden later. | High | Completed | Phase 1 | Admin workflow is functional.
3 | Menu, table, and QR management | Completed | Admin menu category/item management, table CRUD, QR token regeneration, public QR menu lookup, QR UI page, Postman/cURL artifacts. | Public branchId menu lookup remains as foundation/testing route. | High | Completed | Phase 2 | Production-oriented QR path is /api/v1/public/qr/{qrToken}.
4 | Customer ordering experience | Completed | Public cart, customer fields, order submission, confirmation, previous orders on device, order tracking API, mobile-first QR menu UI. | Apply deployed DB migrations where required. | High | Completed | Phase 3 | Core customer flow is implemented.
5 | Staff operations and realtime workflows | Completed | Admin kitchen dashboard, order status updates, SignalR staff updates, waiter-call public API/UI, admin waiter-call board. | Deploy latest migrations before using on deployed DBs. | High | Completed | Phase 4 | Kitchen and waiter-call workflows are ready for validation.
6 | Local demo and smoke validation | Completed | Local DB runner, Qrave demo seed, demo owner, branch/table/menu, runtime API smoke test, frontend production runtime check. | Commit current local fixes after validation. | High | Completed | Phase 5 | Local demo token is demo-table-1.
7 | Integration testing and QA hardening | Pending | Unit tests and smoke tests exist. | Add SQL Server integration tests for stored procedures and API/database flows: seed setup, QR lookup, order create/tracking, admin status updates, waiter calls. | High | 3-5 days | Stable local DB runner | This is the recommended next project task.
8 | Deployment readiness | Pending | Local runner and migrations exist. | Add production/deployment migration runner; confirm staging/prod env config for SQL, JWT, frontend API URL, SignalR URL, CORS, secrets. | High | 2-4 days | Phase 7 | Needed before reliable staging/prod rollout.
9 | Staging deployment and acceptance testing | Pending | Runtime smoke checks proven locally. | Deploy backend/database/frontend to staging; run health, login, QR menu, order, tracking, kitchen, waiter-call, and SignalR checks. | High | 3-5 days | Phase 8 | Use real staging URLs and production-like DB.
10 | Production launch preparation | Pending | Core product workflows exist. | Set monitoring/logging, backups, migration rollback plan, domain/SSL, production QR URL strategy, production smoke checklist, launch checklist. | High | 3-5 days | Phase 9 | Production readiness gate.
11 | Post-launch product improvements | Pending | Initial SaaS flow exists. | Improve tenant onboarding, branch/table setup UX, QR print/download polish, reporting, role permissions, billing/subscription planning, customer retention features. | Medium | Ongoing | Phase 10 | Plan after first stable launch.

## Completed
Phase | Completed Work | Business Value | Verification
0 | Project skeleton, docs, Docker, API health, frontend skeleton | Created maintainable starting point | Backend build and health endpoint verified
1 | SQL tables/procedures/indexes, repositories, services, validation, result model | Core data and business layer ready | Unit tests and builds passed
2 | Auth, JWT, tenant context, protected admin APIs, admin branch UI | Restaurant owner can log in and manage branches | Auth/unit/runtime checks passed
3 | Menu/table/QR management and public QR menu | Admin can prepare menus and table QR links | Frontend builds and public fallback/runtime checks passed
4 | Customer cart, order placement, confirmation, previous orders, tracking | Customer can order from QR | Frontend builds and backend tests passed
5 | Kitchen dashboard, order statuses, SignalR, waiter calls | Staff can manage live orders and service requests | Build/test/smoke checks passed
6 | Local DB runner, demo seed, local API/frontend smoke validation | Demo environment is repeatable | Local smoke test passed on API and frontend

## Pending Backlog
Item | Phase | Status | Priority | Why It Matters | Suggested Owner | Estimate | Dependency
Commit current local changes after validation | 6 | In progress | High | Locks in QR demo token fix and dev script changes | Developer | 0.5 day | Backend tests and frontend build
SQL Server integration tests | 7 | Pending | High | Protects stored procedures and DB-backed workflows from regressions | Backend developer | 3-5 days | Local DB runner
Production/deployment migration runner | 8 | Pending | High | Avoids manual and missed SQL migrations in deployed environments | Backend/DevOps | 2-3 days | Integration tests preferred
Environment configuration hardening | 8 | Pending | High | Prevents auth, CORS, SignalR, and API URL deployment issues | Backend/Frontend/DevOps | 1 day | Target staging/prod details
Staging deployment | 9 | Pending | High | First production-like validation | DevOps | 1-2 days | Migration runner and env config
Staging acceptance smoke test | 9 | Pending | High | Confirms customer and staff workflows end-to-end | QA/Developer | 2-3 days | Staging deployment
Production observability and backups | 10 | Pending | High | Required for safe launch and support | DevOps | 1-2 days | Production infra
Production launch checklist | 10 | Pending | High | Makes release steps repeatable and auditable | Project lead | 1 day | Staging acceptance
Remove or hide foundation tenantId route APIs | 10 | Pending | Medium | Reduces legacy API surface before launch | Backend developer | 1-2 days | Admin tenant-context APIs stable
Investigate Next.js dev server HTTP 500 | 11 | Pending | Medium | Improves local developer workflow | Frontend developer | 1-2 days | Next.js 16 tooling behavior
Fix Next.js lint script behavior | 11 | Pending | Medium | Restores standard frontend lint workflow | Frontend developer | 0.5-1 day | Next.js 16 CLI behavior
Tenant onboarding UX | 11 | Pending | Medium | Makes SaaS setup easier for real restaurants | Product/Frontend | TBD | Production feedback
QR print/download polish | 11 | Pending | Medium | Helps restaurants deploy table QR codes | Frontend developer | TBD | Production QR URL strategy